## Slide 1: Pathways and Processes
Developing JHU’s DEI Strategic Plan
Dr. Emil L. Cunningham, Assistant Vice Provost for Diversity and Inclusion & Deputy Chief Diversity Officer, Johns Hopkins University
Erin Fox, PMP, Senior Manager, Strategic Initiatives, Johns Hopkins University
Notes: 1

## Slide 2: No slide title
“…the most important capital that any university has, human capital1.”
1 Young, Anderson, & Stewart (2015)
Notes: 2

## Slide 3: Agenda
Session Objectives
Planning to Strategic Plan
Strategic Planning
Refining the Plan
Building Capacity
Questions
Notes: 1

## Slide 4: Planning to Strategic Plan

## Slide 5: Planning to Strategic Plan
Admin 101 Series: How to Plan for Strategic Planning*
  Convene a pre-planning group
  “Establish an agreed-upon constitution of how committees will be run”
  Choose committee leadership wisely –
    Expertise
    Objective perspective
    Interpersonal skills
    Available time
    Timely
  Support the people leading these efforts – work release
*Perlmutter, B.D., 2019 Admin 101: How to Plan for Strategic Planning. The Chronicle of Higher Education. Retrieved rom from https://www-chronicle-com.proxy1.library.jhu.edu/article/admin-101-how-to-plan-for-strategic-planning/
Notes: 3

## Slide 6: Planning to Strategic Plan: Context
Initial Roadmap was concluding
New Chief Diversity Officer
Beginning months of the COVID-19 pandemic
A moment of racial reckoning in America
https://www.cnn.com/2020/09/04/us/blm-protests-peaceful-report-trnd/index.html
https://news.yale.edu/2021/10/11/widespread-masking-encourages-others-wear-masks
Notes: 2

## Slide 7: Planning to Strategic Plan: Our Initial Roadmap Process
Identify Roadmap 2020 Task Force members
Charge meeting
Dual retreat with Diversity Leadership Council (DLC) to identify work groups
Formation of work groups
Work Groups develop recommendations
Work with University Leadership to create pillars based on recommendations
Open comment and socialization period
Continued refinement
Endorsement by Board of Trustees
Rollout DEI Strategic Plan

## Slide 8: Roadmap 2020 Task Force Timeline and Deliverables

## Slide 9: Planning to Strategic Plan: Our Initial Roadmap Process
Primary Objective
Develop a set of recommendations with measurable goals and accountabilities that highlight new approaches and collaborations within and beyond our academic community aimed at ensuring more concrete progress over the next five years.

## Slide 10: Planning to Strategic Plan: Identifying Task force Members
  Who, or what offices, would you invite to serve as co-chairs of select task force workgroups?
  Who, or what office representation, would you invite to be members of the task force work groups?
  What methods of solicitation would you use to invite either population of work group members?
Group work
Notes: 5 - minutes

## Slide 11: Strategic Planning

## Slide 12: Strategic Planning
Admin 101 Series: How to Manage the Strategic Planning Process*
  Strategic Planning Goals
    Realistic objectives that can be accomplished within a set period of time.
    Arguments, values, and rationales behind those objectives.
    Metrics to mark their success or progress.
    Resources (money, people, materials, facilities) to reach and sustain the objectives.
  Key Points
    Resist the urge to micromanage.
    Make sure the strategic planners are trusted on the campus.
    Plan around your highest priorities.
    Err on the side of specificity.
    Can you really afford what you’re proposing?
    Resolve the contradictions in the final version
*Perlmutter, B.D., 2019 Admin 101: How to Manage the Strategic-Planning Process. The Chronicle of Higher Education. Retrieved from https://www-chronicle-com.proxy1.library.jhu.edu/article/admin-101-how-to-manage-the-strategic-planning-process/
Notes: 3

## Slide 13: Strategic Planning: Roadmap 2020 Task Force
Senior Institutional Leaders (e.g., Vice Provosts, Vice Presidents, etc.)
Deans
Faculty (including department heads/chairs)
Staff
Students (undergrad and graduate students)
Alumni
Postdocs
Community partners
Institutional Accountability
Student Success
  Graduate
  Undergraduate
Faculty Diversity Initiative
Pathways to Staff Advancement
Community Engagement
Alumni Engagement
Training and Development
Task Force Members
Workgroups

## Slide 14: Strategic Planning: Engaging Affiliates
Affiliation
Division
Community
Leaders

## Slide 15: Strategic Planning: Task Force Guiding Principles
Radical transparency
Data-driven
Targeted resource allocation
Systems-based approach
Hearts and minds
Institutional accountability
Bold/innovative/deeper
Clear metrics and Outcomes
Less is more

## Slide 16: Integrating Systems and Design Thinking
Systemic Design Toolkit (Kristel van Ael of Namahnlick)

## Slide 17: Strategic Planning: Listening To the System – Staff Development
Staff composition reports
  Public documents that examine the composition of job classification and division by demography
Internal efforts
  Produced results, but more effort was needed
Similar to our peers
  But not the make-up of Baltimore
Notes: External Models - Netflix

## Slide 18: Strategic Planning: Understanding the System - Addressing Root Causes
Faculty Diversity
Many in the STEM fields argue the pool is small (# of PhDs in STEM fields per year)
If the pool is small (root cause), there are multiple solutions
  Make the pool bigger (VTSI)
  Make the pool more robust
  Invest in growing the pool
Led to dual investments into Graduate and Faculty development
Increased opportunities for scholars from underrepresented backgrounds
Increased Ph.Ds granted to scholars from underrepresented backgrounds
Increased pool of faculty from underrepresented backgrounds
Increased opportunities for development and retention for faculty from underrepresented backgrounds
Increased opportunities for faculty from underrepresented backgrounds to collaborate with students from underrepresented backgrounds

## Slide 19: Strategic Planning: Identifying Your Systems
Group Work
  What systems could your strategic plan help address?
  Are there easily identifiable root cause issues (e.g., barriers to inclusion) within these systems?
  What are the intersections of your institution's DEI principles with the systems and root cause issues you've identified?
Notes: 5 – minutes
If you don’t know the root cause of an issue, what data do you need to better understand the issue?

## Slide 20: Refining The Plan

## Slide 21: Refining the Plan: Task Force Review Cycles
Cycle 1
  3-5 preliminary goals per workgroup
    Include metrics
    Identify responsible agents
    Offer anticipated timeline
Cycle 2
  2-3 refined goals per workgroup
    Include metrics
    Refinement of responsible agents
    Clearer delineation of timeline
    Recommend assessment plan
Cycle 3
  2-3 finalized goals per work group inclusive of:
    Defined metrics
    Identified and named responsible agents
    Explicit timeline
    Robust assessment plan
    Anticipated budget

## Slide 22: What we received... Roadmap Task Force Recommendations—Disposition in Second Roadmap Goals
https://diversity.jhu.edu/second-jhu-roadmap-on-diversity-equity-and-inclusion/roadmap-task-force-recommendations-disposition-in-second-roadmap-goals/

## Slide 23: No title slide
65 Recommendations!!!!!

## Slide 24: Refning the Plan: Coming to a Consensus
  How would you whittle this list down?
  Who do you need input from?
  How would you solicit feedback?
Group work
Notes: 5 minutes

## Slide 25: Refining the Plan: Identifying and Prioritizing Strategic Planning Efforts
Community feedback
  Focus groups and interviews
  Voting on priorities
  Feedback on draft plan
Evidence/Research-based
Leadership and Institutional Priorities
Political Environment
Data
  Composition Reports
  Survey results
Community Feedback
Data
Institutional Priorities
Final Goals

## Slide 26: Refining the Plan: Commitment without currency...
Putting our money where our heart is
  Key Initiatives
    Vivien Thomas Scholars Initiative ($150M)
    Target of Opportunity Program => Fannie Gaston Johannson Faculty of Excellence Program ($50M)
    Staff Career Architecture ($10M)
    DEI Graduate Student Ambassadors ($TBD)
    Graduate Student Relocation funds ($TBD)
    Community Academic Partnerships ($5M)
  Additional fund requests
    Student DEI lifecycle ($TBD)
    Student diversity and inclusion space ($TBD)
Building DEI Staffing Infrastructure
  4 Academic DEI Deans
  12 new central DEI office positions
  4 new student DEI focused positions
  2 new operational DEI focused positions with alignment to central DEI office
Financial Accountability
  Institution-wide DEI spend tracking
  Roadmap-related spend tracking
Notes: We had a plan without the process for financial investments
Commitment without currency is counterfeit

## Slide 27: Building Capacity
Leverage Existing Resources
Develop New Resources
Continual Advocacy
VectorStock.com/9645765
Notes: We now have goals!
  But how do we get there?
    Existing Resources
    New Resources
Now we have resources!
  But what to do with them?
    D&I Practitioners Group
    Diversity Leadership Institute
      Developing local and central infrastructure
      Learning and Support
Being in the room
  Advocacy
  Sharing successes and needs

## Slide 28: Questions
rd.com/list/mensa-quiz/

## Slide 29: Thank you!
Dr. Emil L. Cunningham
Assistant Vice Provost for Diversity and Inclusion & Deputy Chief Diversity Officer
Johns Hopkins University
emil1@jhu.edu
Erin Fox, PMP
Senior Manager, Strategic Initiatives
Johns Hopkins University
erinfox@jhu.edu